## Sheet1
Issue ID | Issue Type | Module | Summary | Assignee | Reporter | Priority | Status | Created Date | Resolved Date | Root Cause
HZJIRA-1001 | Improvement | BW | BW improvement identified in UAT phase | Subhasis | Kiran | Medium | In Progress | 2025-01-15 |  | Custom code defect
HZJIRA-1002 | Bug | QM | QM bug identified in UAT phase | Kiran | Kiran | Critical | Open | 2025-02-25 |  | Integration failure
HZJIRA-1003 | Improvement | FI | FI improvement identified in UAT phase | Amit | Kiran | Medium | Open | 2025-02-15 |  | Data inconsistency
HZJIRA-1004 | Bug | EWM | EWM bug identified in UAT phase | Sujaan | Neha | High | Reopened | 2025-01-30 |  | Integration failure
HZJIRA-1005 | Task | HCM | HCM task identified in UAT phase | Anjali | Raja | Low | Closed | 2025-01-12 | 2025-01-19 | Dependency failure
HZJIRA-1006 | Bug | QM | QM bug identified in UAT phase | Amit | Subhasis | Critical | Resolved | 2025-03-30 | 2025-04-09 | Data inconsistency
HZJIRA-1007 | Change Request | PP | PP change request identified in UAT phase | Raja | Kiran | Low | Closed | 2025-01-02 | 2025-01-08 | Transport issue
HZJIRA-1008 | Change Request | MM | MM change request identified in UAT phase | Subhasis | Sujaan | Medium | Reopened | 2025-03-28 |  | Master data gap
HZJIRA-1009 | Change Request | FI | FI change request identified in UAT phase | Hari | Raja | Medium | Reopened | 2025-02-25 |  | Integration failure
HZJIRA-1010 | Change Request | HCM | HCM change request identified in UAT phase | Neha | Neha | Critical | Open | 2025-02-24 |  | Dependency failure
HZJIRA-1011 | Change Request | FI | FI change request identified in UAT phase | Subhasis | Subhasis | High | Resolved | 2025-01-30 | 2025-02-06 | Authorization error
HZJIRA-1012 | Task | HCM | HCM task identified in UAT phase | Neha | Sujaan | Low | Reopened | 2025-02-23 |  | Configuration missing
HZJIRA-1013 | Improvement | EWM | EWM improvement identified in UAT phase | Raja | Anjali | Critical | Closed | 2025-03-25 | 2025-03-31 | Integration failure
HZJIRA-1014 | Change Request | QM | QM change request identified in UAT phase | Raja | Neha | Critical | Open | 2025-03-11 |  | Integration failure
HZJIRA-1015 | Task | MM | MM task identified in UAT phase | Amit | Kiran | Medium | Closed | 2025-02-21 | 2025-03-01 | Performance bottleneck
HZJIRA-1016 | Task | MM | MM task identified in UAT phase | Hari | Amit | Medium | Open | 2025-01-20 |  | Transport issue
HZJIRA-1017 | Improvement | BW | BW improvement identified in UAT phase | Kiran | Subhasis | Low | Closed | 2025-01-30 | 2025-02-04 | Transport issue
HZJIRA-1018 | Bug | HCM | HCM bug identified in UAT phase | Raja | Amit | Critical | Reopened | 2025-01-01 |  | Data inconsistency
HZJIRA-1019 | Change Request | SD | SD change request identified in UAT phase | Anjali | Kiran | Critical | Reopened | 2025-02-11 |  | Data inconsistency
HZJIRA-1020 | Bug | BW | BW bug identified in UAT phase | Amit | Sujaan | Critical | In Progress | 2025-02-05 |  | Master data gap
HZJIRA-1021 | Bug | MM | MM bug identified in UAT phase | Subhasis | Hari | High | Closed | 2025-01-21 | 2025-01-25 | Master data gap
HZJIRA-1022 | Task | MM | MM task identified in UAT phase | Neha | Subhasis | High | In Progress | 2025-01-26 |  | Data inconsistency
HZJIRA-1023 | Improvement | EWM | EWM improvement identified in UAT phase | Neha | Neha | High | Open | 2025-03-06 |  | Performance bottleneck
HZJIRA-1024 | Improvement | BW | BW improvement identified in UAT phase | Anjali | Sujaan | Low | Closed | 2025-02-20 | 2025-02-25 | Master data gap
HZJIRA-1025 | Bug | BW | BW bug identified in UAT phase | Sujaan | Amit | Low | Closed | 2025-03-26 | 2025-03-28 | Integration failure
HZJIRA-1026 | Improvement | FI | FI improvement identified in UAT phase | Hari | Kiran | Critical | Resolved | 2025-01-23 | 2025-01-28 | Testing oversight
HZJIRA-1027 | Bug | MM | MM bug identified in UAT phase | Sujaan | Hari | Medium | Closed | 2025-01-23 | 2025-01-31 | Data inconsistency
HZJIRA-1028 | Change Request | FI | FI change request identified in UAT phase | Neha | Raja | High | Closed | 2025-03-06 | 2025-03-07 | Performance bottleneck
HZJIRA-1029 | Task | PP | PP task identified in UAT phase | Hari | Neha | Medium | Reopened | 2025-02-18 |  | Dependency failure
HZJIRA-1030 | Bug | PP | PP bug identified in UAT phase | Amit | Subhasis | Medium | Open | 2025-02-10 |  | Master data gap
HZJIRA-1031 | Task | QM | QM task identified in UAT phase | Neha | Subhasis | Medium | Closed | 2025-03-29 | 2025-03-31 | Master data gap
HZJIRA-1032 | Task | BW | BW task identified in UAT phase | Subhasis | Sujaan | Low | Open | 2025-01-16 |  | Transport issue
HZJIRA-1033 | Change Request | FI | FI change request identified in UAT phase | Raja | Amit | High | In Progress | 2025-02-22 |  | Custom code defect
HZJIRA-1034 | Bug | PP | PP bug identified in UAT phase | Kiran | Neha | Medium | Resolved | 2025-01-23 | 2025-01-25 | Integration failure
HZJIRA-1035 | Change Request | HCM | HCM change request identified in UAT phase | Amit | Sujaan | Low | Resolved | 2025-03-29 | 2025-03-30 | Dependency failure
HZJIRA-1036 | Improvement | FI | FI improvement identified in UAT phase | Subhasis | Anjali | Low | Closed | 2025-02-28 | 2025-03-06 | Testing oversight
HZJIRA-1037 | Bug | FI | FI bug identified in UAT phase | Hari | Neha | Low | Closed | 2025-03-16 | 2025-03-17 | Configuration missing
HZJIRA-1038 | Change Request | QM | QM change request identified in UAT phase | Sujaan | Raja | Medium | Open | 2025-01-16 |  | Testing oversight
HZJIRA-1039 | Bug | MM | MM bug identified in UAT phase | Raja | Hari | Medium | Closed | 2025-01-20 | 2025-01-28 | Authorization error
HZJIRA-1040 | Bug | MM | MM bug identified in UAT phase | Neha | Amit | Low | Open | 2025-01-30 |  | Performance bottleneck
HZJIRA-1041 | Improvement | QM | QM improvement identified in UAT phase | Amit | Hari | Critical | Resolved | 2025-03-11 | 2025-03-16 | Data inconsistency
HZJIRA-1042 | Change Request | PP | PP change request identified in UAT phase | Amit | Raja | Low | Closed | 2025-04-01 | 2025-04-04 | Integration failure
HZJIRA-1043 | Bug | MM | MM bug identified in UAT phase | Raja | Amit | Medium | Closed | 2025-01-28 | 2025-02-07 | Dependency failure
HZJIRA-1044 | Task | MM | MM task identified in UAT phase | Hari | Hari | High | Reopened | 2025-02-03 |  | Transport issue
HZJIRA-1045 | Improvement | QM | QM improvement identified in UAT phase | Kiran | Neha | Critical | Reopened | 2025-01-31 |  | Configuration missing
HZJIRA-1046 | Bug | FI | FI bug identified in UAT phase | Subhasis | Amit | High | Open | 2025-02-23 |  | Performance bottleneck
HZJIRA-1047 | Change Request | EWM | EWM change request identified in UAT phase | Anjali | Raja | High | Reopened | 2025-02-12 |  | Master data gap
HZJIRA-1048 | Task | HCM | HCM task identified in UAT phase | Amit | Anjali | Critical | Resolved | 2025-01-08 | 2025-01-15 | Data inconsistency
HZJIRA-1049 | Improvement | PP | PP improvement identified in UAT phase | Amit | Raja | Medium | Open | 2025-02-24 |  | Performance bottleneck
HZJIRA-1050 | Task | MM | MM task identified in UAT phase | Subhasis | Subhasis | Critical | In Progress | 2025-02-03 |  | Configuration missing